## Logframe
Level | Result statement | Indicator | Baseline | Target | Means of Verification | Assumptions
Goal | Women’s economic resilience supported through inclusive financial services | Women reporting ability to meet an unexpected expense / manage a shock | Baseline survey; set after district selection | Target set after baseline | Endline survey | Economic conditions and service availability remain adequate
Outcome 1 | Women gain access to suitable financial services | Women who have an account that they themselves use | NFHS-4 district baseline available after district selection and crosswalk | Set after validation | NFHS factsheets; field survey | Accounts remain accessible and functional
Outcome 2 | Women exercise control over account use and transactions | Share of account holders who can transact independently | Field baseline pending | Set after baseline | Household survey; transaction recall | Respondents can answer privately and safely
Outcome 3 | Digital access and confidence improve | Women who themselves use a mobile phone; digital task competency | NFHS baseline pending common indicator confirmation | Set after baseline | NFHS factsheets; skills assessment | Network, devices and accessible support are available
Output 1 | Local agent and bank support improves | Functional service points and resolution rate | Baseline mapping pending | Set after mapping | Service point audit; grievance log | Banks and BC networks cooperate
Output 2 | Women receive practical financial capability support | Participants completing modules; knowledge change | Programme baseline pending | Set after baseline | Attendance and pre/post assessment | Content is accessible and locally relevant
Output 3 | Peer and referral mechanisms are active | Active groups and completed referrals | Baseline pending | Set after district selection | Group records and referral tracking | Community partners are trusted
Activities | Map service availability; co-design training; provide assisted practice; establish referral/grievance pathways; monitor safe use | Delivery completion and quality checks | Not applicable | Quarterly milestones after inception | Activity records; supervision checklists | Staffing and procurement occur on time